## Slide 1: Zanmi Kafe: All The Reasons We Could FAIL

## Slide 2: What’s hiding behind the balloon? … it’s failure

## Slide 3: Time Management
We do not finish our project because of poor time management.

## Slide 4: Data Errors and Malfunctions The Issue: Why It Failed:
Incorrect outputs and data or code doesn’t run (dashboard doesn’t work)
We can’t get shiny app or other R related code, Github to work
We pick the wrong allometric equation
Use wrong conversion
Lose raw data
→ not checking data as we go
→ not checking code as we go or being careful
→ not checking with client
→ not being careful and checking our work
→ didn’t back up data or keep the raw data

## Slide 5: Communication Inefficiencies The Issue: Why It Failed:
Not following guidance of or communicating frequently with the client
We aren’t considerate or communicate our problems
We don’t know what we don’t know
Fail to establish a meeting schedule and direct line to client
Don’t discuss our skill sets upfront
Create an undesired end product for our client
We develop inter-team beef
We don’t know when to ask for help
Unable to reach client
Assigning someone a task they don’t understand

## Slide 6: Other Bad Things The Issue: Why It Failed:
Someone loses motivation
Faulty internet or devices
→ Not doing self-care
→ Not showing up early enough to check devices

## Slide 7: Additionally:
Zombie apocalypse (Finland or US)
Global pandemic
Spilled coffee on laptop (Simultaneous or sequential)
Spencer Hall spontaneously combusts, Nika holds our virtual funeral
Finland spontaneously combusts, we hold Nika’s virtual funeral
Our microchips activate and we become robot soldiers
Someone gets salmonella
  Or another debilitating disease
THANKS! Questions?